## Executive_Summary
Metric | Value
Project Name | SauceDemo Manual Testing
Test Type | Manual Testing
Module Tested | Login, Products, Cart, Checkout, UI
Start Date | 2026-07-14
End Date | 2026-07-16
Executed By | QA Team
Environment | Chrome 114.0, Windows 11
Total Test Cases | 45
Executed | 45
Passed | 45
Failed | 0
Blocked | 0
Not Executed | 0
Pass Percentage | 100%
Bugs Found | 7
Critical Bugs | 0
High Priority Bugs | 2
Medium Priority Bugs | 3
Low Priority Bugs | 2
Overall Status | PASSED

## Module_wise_Summary
Module | Total | Executed | Passed | Failed | Blocked | Pass % | Bugs Found
Login Module | 14 | 14 | 14 | 0 | 0 | 100% | 5
Products Module | 16 | 16 | 16 | 0 | 0 | 100% | 0
Cart Module | 5 | 5 | 5 | 0 | 0 | 100% | 0
Checkout Module | 7 | 7 | 7 | 0 | 0 | 100% | 0
UI Testing | 3 | 3 | 3 | 0 | 0 | 100% | 2
Total | 45 | 45 | 45 | 0 | 0 | 100% | 7

## Priority_Wise_Distribution
Priority | Total | Passed | Failed | Pass %
High | 28 | 28 | 0 | 100%
Medium | 12 | 12 | 0 | 100%
Low | 5 | 5 | 0 | 100%
Total | 45 | 45 | 0 | 100%

## Detailed_Execution_Log
Test Case ID | Module | Test Scenario | Priority | Status | Execution Date | Executed By | Bug ID
TC_LOGIN_001 | Login | Verify login with valid credentials | High | Pass | 2026-07-14 | Rojina Adhikari | -
TC_LOGIN_002 | Login | Verify login with invalid credentials | High | Pass | 2026-07-14 | Rojina Adhikari | BUG-001
TC_LOGIN_003 | Login | Verify login with empty credentials | High | Pass | 2026-07-14 | Rojina Adhikari | BUG-002
TC_LOGIN_004 | Login | Verify login with locked-out user | Medium | Pass | 2026-07-14 | Rojina Adhikari | BUG-003
TC_LOGIN_005 | Login | Verify login with valid username and empty password | High | Pass | 2026-07-14 | Rojina Adhikari | BUG-002
TC_LOGIN_006 | Login | Verify login with valid username and invalid password | High | Pass | 2026-07-14 | Rojina Adhikari | BUG-001, BUG-007
TC_LOGIN_007 | Login | Verify login with problem user | Low | Pass | 2026-07-14 | Rojina Adhikari | BUG-004
TC_LOGIN_008 | Login | Verify login with performance glitch user | Medium | Pass | 2026-07-14 | Rojina Adhikari | BUG-005
TC_LOGIN_009 | Login | Verify login with error user | Low | Pass | 2026-07-14 | Rojina Adhikari | BUG-004
TC_LOGIN_010 | Login | Verify login with visual user | Low | Pass | 2026-07-14 | Rojina Adhikari | BUG-006
TC_LOGIN_011 | Login | Verify password masking | Medium | Pass | 2026-07-14 | Rojina Adhikari | -
TC_LOGIN_012 | Login | Verify login using Enter key | Low | Pass | 2026-07-14 | Rojina Adhikari | -
TC_LOGIN_013 | Login | Verify login with copied username | Low | Pass | 2026-07-14 | Rojina Adhikari | -
TC_LOGIN_014 | Login | Verify login with copied password | Low | Pass | 2026-07-14 | Rojina Adhikari | -
TC_PROD_001 | Products | Verify product grid layout | High | Pass | 2026-07-15 | Rojina Adhikari | -
TC_PROD_002 | Products | Verify product cards display | High | Pass | 2026-07-15 | Rojina Adhikari | -
TC_PROD_003 | Products | Verify number of products displayed | High | Pass | 2026-07-15 | Rojina Adhikari | -
TC_PROD_004 | Products | Verify product images display | High | Pass | 2026-07-15 | Rojina Adhikari | -
TC_PROD_005 | Products | Verify product titles display | High | Pass | 2026-07-15 | Rojina Adhikari | -
TC_PROD_006 | Products | Verify product descriptions display | High | Pass | 2026-07-15 | Rojina Adhikari | -
TC_PROD_007 | Products | Verify product prices display | High | Pass | 2026-07-15 | Rojina Adhikari | -
TC_PROD_008 | Products | Verify Add to Cart button display | High | Pass | 2026-07-15 | Rojina Adhikari | -
TC_PROD_009 | Products | Verify Add to Cart functionality | High | Pass | 2026-07-15 | Rojina Adhikari | -
TC_PROD_010 | Products | Verify Remove button functionality | High | Pass | 2026-07-15 | Rojina Adhikari | -
TC_PROD_011 | Products | Verify cart badge counter updates | Medium | Pass | 2026-07-15 | Rojina Adhikari | -
TC_PROD_012 | Products | Verify filter dropdown options | Medium | Pass | 2026-07-15 | Rojina Adhikari | -
TC_PROD_013 | Products | Verify sort by Name (A to Z) | Medium | Pass | 2026-07-15 | Rojina Adhikari | -
TC_PROD_014 | Products | Verify sort by Name (Z to A) | Medium | Pass | 2026-07-15 | Rojina Adhikari | -
TC_PROD_015 | Products | Verify sort by Price (Low to High) | Medium | Pass | 2026-07-15 | Rojina Adhikari | -
TC_PROD_016 | Products | Verify sort by Price (High to Low) | Medium | Pass | 2026-07-15 | Rojina Adhikari | -
TC_CART_001 | Cart | Verify cart page displays items correctly | High | Pass | 2026-07-15 | Rojina Adhikari | -
TC_CART_002 | Cart | Verify remove from cart functionality | High | Pass | 2026-07-15 | Rojina Adhikari | -
TC_CART_003 | Cart | Verify Continue Shopping button | High | Pass | 2026-07-15 | Rojina Adhikari | -
TC_CART_004 | Cart | Verify Checkout button navigation | High | Pass | 2026-07-15 | Rojina Adhikari | -
TC_CART_005 | Cart | Verify empty cart message | Medium | Pass | 2026-07-15 | Rojina Adhikari | -
TC_CHK_001 | Checkout | Verify checkout information form display | High | Pass | 2026-07-15 | Rojina Adhikari | -
TC_CHK_002 | Checkout | Verify checkout with valid information | High | Pass | 2026-07-15 | Rojina Adhikari | -
TC_CHK_003 | Checkout | Verify checkout with missing First Name | High | Pass | 2026-07-15 | Rojina Adhikari | -
TC_CHK_004 | Checkout | Verify checkout with missing Last Name | High | Pass | 2026-07-15 | Rojina Adhikari | -
TC_CHK_005 | Checkout | Verify checkout with missing Zip Code | High | Pass | 2026-07-15 | Rojina Adhikari | -
TC_CHK_006 | Checkout | Verify checkout overview display | High | Pass | 2026-07-15 | Rojina Adhikari | -
TC_CHK_007 | Checkout | Verify total calculation | High | Pass | 2026-07-15 | Rojina Adhikari | -
TC_UI_001 | UI Testing | Verify Login page UI elements | Medium | Pass | 2026-07-15 | Rojina Adhikari | -
TC_UI_002 | UI Testing | Verify Products page UI elements | Medium | Pass | 2026-07-15 | Rojina Adhikari | -
TC_UI_003 | UI Testing | Verify responsive design | Medium | Pass | 2026-07-15 | Rojina Adhikari | -

## Status_Dashboard
Pass Rate Visualization
Overall Pass Rate: 100% (45/45)
100% Pass
0% Fail
0% Blocked
Module-wise Pass Rate | Column 1
Login Module | 100%
Products Module | 100%
Cart Module | 100%
Checkout Module | 100%
UI Testing | 100%

## Bug_Summary
Bug ID | Title | Severity | Priority | Status | Test Case ID
BUG-001 | Incorrect Error Message Format for Invalid Credentials | Medium | High | Open | TC_LOGIN_002
BUG-002 | Incorrect Error Message Format for Empty Credentials | Medium | High | Open | TC_LOGIN_003
BUG-003 | Incorrect Error Message Format for Locked-Out User | Medium | Medium | Open | TC_LOGIN_004
BUG-004 | Broken Product Images for Problem User | Medium | Medium | Open | TC_LOGIN_007
BUG-005 | Performance Delay for Performance Glitch User | Low | Medium | Open | TC_LOGIN_008
BUG-006 | Distorted UI for Visual User | Low | Low | Open | TC_LOGIN_010
BUG-007 | Typographical Error in Test Data | Low | Low | Open | TC_LOGIN_006

## Environment_Details
Component | Details
Application URL | https://www.saucedemo.com/
Browser | Chrome 114.0
Operating System | Windows 11
Screen Resolution | 1920 x 1080
Network Speed | 100 Mbps
Test Data | Valid credentials, Invalid credentials, Checkout data
Tools Used | GitHub, Excel, Chrome DevTools

## Risk_Summary
Risk/Issue | Impact | Mitigation | Status
Error message inconsistency | User confusion | Fix error message format | Open
Performance delay | Poor user experience | Optimize performance | Open
Broken images | Visual regression | Fix image loading | Open
UI distortion | Inconsistent UX | Fix UI rendering | Open

## Recommendations
Priority | Recommendation | Bug ID
High | Remove "Epic sadface:" prefix from invalid credentials error | BUG-001
High | Remove "Epic sadface:" prefix from empty credentials error | BUG-002
Medium | Remove "Epic sadface:" prefix from locked user error | BUG-003
Medium | Fix broken images for problem_user | BUG-004
Medium | Optimize performance for performance_glitch_user | BUG-005
Low | Fix UI distortion for visual_user | BUG-006
Low | Fix typo in test data | BUG-007